## Format description HU
HU-Eutobyte Framework Matrix (User Stories)
ITEM | ISSUE | WHAT (NEED) | WHY (SOLUTION) | FOR WHOM (USER) | HOW (TASK DESCRIPTION) | MADE BY (PROG. RESP.) | HOW LONG (ESTIMATED IN HRS) | DATE OF DELIVERY | PRIORITY | STATUS | PROOF (HOW TO VERIFY) | COMMENTS | STORY NAME
REQ001 | Perform user registration | Enter data | Store user record | Client | Request the name, surname, ID and address | Rommel Zambrano | 2 | 2022-05-27 | high | Finished | Data Validation Unit Test (User Registration) |  | Request data from the user
REQ002 | Add specific products to the minimarket database | enter products to the DB | Store product record in category | Client | Request Product ID, Name, Description, Quantity, Price | Ismael Salazar | 4 | 2022-05-28 | high | Finished | Unit test of data entered correctly in MondoBD |  | Add products to the system
REQ003 | Calculate the total number of products in the market | Calculate the total number of existing products | Register the total of products | Client | Calculate the total of market products without categorizing | Ismael Salazar | 4 | 2022-05-29 | high | Finished | Viewing the total number of products using the corresponding business rule |  | Calculate total product quantity
REQ004 | Calculate profits generated on product sales | Calculate sales profit | Record profits generated from sales | Client | Calculate the total profit from the sale of products of various types | Rommel Zambrano | 4 | 2022-05-29 | high | Finished | View the sales profits generated by the business rule |  | Calculate product earnings
REQ005 | Verify with a service the payment of the products | Validate the payment of the products | Verify that the purchase of a product has been created and its price is paid | Client | Validate the payment through an invoice with several requested data | Brandon Saltos | 3 | 2022-06-20 | high | Finished | An ok message is displayed on the screen with the generated payment record |  | Validate the type and amount of payment
REQ006 | Modify the products uploaded to the base | Change the product entered to the DB | Modify a product that has been uploaded for purchase | Product | Exchange the product for a different one of our choice | Rommel Zambrano | 2 | 2022-06-20 | high | Finished | View the purchase data with a changed product |  | Modify product in the DB
REQ007 | Delete the product uploaded to the base | Remove a product that has been added to the DB | Modify the purchase parameters by deleting the product | Product | Remove the product from the list that was added before. | Rommel Zambrano | 2 | 2022-06-20 | high | Finished | View the data without the product field that was removed |  | Remove product from list
REQ008 | Create a product to add to the base | Generates a new product to add to the DB | Modify the list of the DB to view new products | Product | Generate a new product to get new data | Rommel Zambrano | 2 | 2022-06-20 | high | Finished | View the added data in the list of the created database |  | Create a new product
REQ009 | Read the product data that is already in the database | View the data already added to the database | Know all the data already added to the DB | Product | Show all data already added with their names | Rommel Zambrano | 2 | 2022-06-20 | high | Finished | View all the data that has been added |  | Show product details
REQ010 | Create user for the DB | Will generate new user data | Add users to the database list | User | Add users to get new data | Ismael Salazar | 4 | 2022-06-20 | high | Finished | Visualize that a new user is created in the list |  | User creation
REQ011 | Show User created in the DB | It will show the user data in the list | Know all the data of the users of the BD | User | Show all the data of the user that has already been added | Ismael Salazar | 4 | 2022-06-20 | high | Finished | View all the data of the users created |  | show to user
REQ012 | Remove user from our database | Delete data of an existing user | Modify the parameters of the purchase by deleting the user | User | Delete the user from the list that is done before | Ismael Salazar | 4 | 2022-06-20 | high | Finished | It shows that the created user has been deleted |  | Delete User
REQ013 | Update user with new values for the DB | Change data of the added user to update them | Modify user data by changing and updating values | User | change the username for a different one with new data | Ismael Salazar | 4 | 2022-06-20 | high | Finished | Shows that the data of the selected user has been updated |  | update user
REQ014 | Create a supplier for the products of the purchase | Generate a supplier of the products with new data | Add suppliers to the purchase | providers | Add new providers to the list | Luis Ramon | 4 | 2022-06-20 | high | Finished | View the supplier data added correctly |  | Create supplier
REQ015 | Show the created supplier of the products of the purchase | It will show the data of the created provider | Know the data of the respective providers | providers | Show all the data of the added provider | Luis Ramon | 4 | 2022-06-20 | high | Finished | View the data created from all providers |  | show provider
REQ016 | Delete the created provider | It will eliminate the supplier created for the products | Modify the parameters of the purchase by eliminating that method | providers | Delete the selected provider | Luis Ramon | 4 | 2022-06-20 | high | Finished | See that the providers have been eliminated |  | Delete provider
REQ017 | Update provider parameters | Change the data of the chosen provider | Update supplier data by changing values | providers | Change provider values with new ones | Luis Ramon | 4 | 2022-06-20 | high | Finished | View updated supplier data |  | Update provider
REQ018 | Create an invoice for the purchase in the DB | Generate an invoice for the purchase in the DB | Add an invoice to the purchase | invoice | Add new invoices to the list | Brandon Saltos | 4 | 2022-06-20 | high | Finished | Shows that an invoice has been successfully created |  | create invoice
REQ019 | Show purchase invoice in DB | It will show the data of the invoice created in the DB | Know the data of said invoice | invoice | Shows the data of the invoice created previously | Brandon Saltos | 4 | 2022-06-20 | high | Finished | Visualize the data of an invoice correctly |  | Show the created invoice
REQ020 | Delete the purchase invoice in the DB | It will delete the data of an invoice in the DB | Completely delete an invoice created | invoice | Delete the invoice created in the list | Brandon Saltos | 4 | 2022-06-20 | high | Finished | Shows that an invoice has been completely deleted |  | Delete the created invoice
REQ021 | Update purchase invoice in the DB | Update the invoice data in the database | Update invoice data with new values | invoice | Updates the data of a selected invoice, with new | Brandon Saltos | 4 | 2022-06-20 | high | Finished | View a selected invoice with the new updated data |  | Update the created invoice
REQ022
REQ023
REQ024
REQ025

## User Story
USER HISTORY (HU) EuroByte
| ITEM |  | USERNAME |  | STATUS
| REQ010 |  | User |  | Finished
| WEATHER |  | PRIORITY |  | PROG. ANSWER
| 4 |  | high |  | Ishmael Salazar
| THAT | Will generate new user data |  | WHAT FOR | Add users to the database list |  | WHAT | Add users to get new data
| STORY NAME |  | User creation
| TEST |  | Visualize that a new user is created in the list |  |  | COMMENTS | 0